## Gantt
Create a Gantt Chart in this worksheet. Enter title of this project in cell B1. Legend title is in cell I1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | TO-DO LIST APP
Enter Company Name in cell B2. A legend is in cells I2 through AC2.
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell F3 or allow the sample formula to find the smallest date value from the Gantt Data table. Project Start Date: label is in cell D3. | Leader: Lưu Thành Đạt
A Scrolling Increment is in cell F4. Months for the dates in row 5 are displayed starting in cells I4 through cell BL4. Do not modify these cells. They are auto updated based on the project start date in cell F3.
Cells I5 through BL5 contain the day number of the month for the Month represented in the cell block above each date cell and are auto calculated. Do not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule.
A scrollbar is in cells I6 through BL6. The increment for paging through the data is defined as 2 pages at a time and can be configured in the settings for the control bar. To jump forward or backward in the timeline, enter a value of 0 or higher in cell F4. A value of 0 takes you to the beginning of the chart. | [8 empty] | Tháng 9 | [21 empty] | Tháng 10 | [30 empty] | Tháng 11 | [29 empty] | Tháng 12
This row contains headers for the project schedule that follows below them. Navigate from B7 through BL7 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I7 and continues through cell BL7. All project timeline charting is auto generated based on the category, start date and number of days entered in the Milestones table. | Functions | Category | Milestone | Assigned To | Story Point | Start | End | PERIODS | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule. | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [81 empty] | #REF! | #REF! | #REF! | #REF! | [13 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Enter Project information starting in cell B9 through cell G9. Sample data is in cells B9 through G33. Enter Milestone Description, select a Category from the drop-down list, assign someone to the item, enter the progress, start date and number of days for the task to start charting. The next instruction is in cell A34. | MANAGE PROJECT |  |  |  | 20 | 19/10/2020 | 2020-03-11
| C.R.U.D Project | Feature | Milestone_1 | Giang |  | 19/10/2020 | 27/10/2020 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Enter Project information starting in cell B9 through cell G9. Sample data is in cells B9 through G33. Enter Milestone Description, select a Category from the drop-down list, assign someone to the item, enter the progress, start date and number of days for the task to start charting. The next instruction is in cell A34. | MANAGE SECTION |  |  |  | 20 | 19/10/2020 | 2020-03-11
| C.R.U.D Section | Feature | Milestone_1 | Hằng |  | 19/10/2020 | 27/10/2020 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Enter Project information starting in cell B9 through cell G9. Sample data is in cells B9 through G33. Enter Milestone Description, select a Category from the drop-down list, assign someone to the item, enter the progress, start date and number of days for the task to start charting. The next instruction is in cell A34. | MANAGE TASK |  |  |  | 20 | 19/10/2020 | 2020-03-11
| C.R.U.D Task | Feature | Milestone_1 | Nhật Hào |  | 19/10/2020 | 27/10/2020
| Search | Feature | Milestone_1 | Nhật Hào |  | 23/10/2020 | 30/10/2020
| Sort by | Feature | Milestone_1 | Nhật Hào |  | 23/10/2020 | 30/10/2020
| Group by | Feature | Milestone_1 | Nhật Hào |  | 23/10/2020 | 30/10/2020
| Favorite management | Feature | Milestone_1 | Nhật Hào |  | 25/10/2020 | 2020-03-11
| Rich Text | Feature | Milestone_1 | Nhật Hào |  | 25/10/2020 | 2020-03-11
| Set priority | Feature | Milestone_1 | Nhật Hào |  | 25/10/2020 | 2020-03-11
| Set Tag | Feature | Milestone_1 | Nhật Hào |  | 25/10/2020 | 2020-03-11
| Add Website as Task | Feature | Milestone_1 | Nhật Hào |  | 25/10/2020 | 2020-03-11
| Copy & paste multiple lines | Feature | Milestone_1 | Nhật Hào |  | 25/10/2020 | 2020-03-11
| Filter Query | Feature | Milestone_1 | Nhật Hào |  | 25/10/2020 | 2020-03-11
| Drag & Drop | Feature | Milestone_1 | Nhật Hào |  | 25/10/2020 | 2020-03-11
| Undo Task | Feature | Milestone_1 | Nhật Hào |  | 25/10/2020 | 2020-03-11
| Set Layout | Feature | Milestone_1 | Nhật Hào |  | 25/10/2020 | 2020-03-11 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Enter Project information starting in cell B9 through cell G9. Sample data is in cells B9 through G33. Enter Milestone Description, select a Category from the drop-down list, assign someone to the item, enter the progress, start date and number of days for the task to start charting. The next instruction is in cell A34. | MANAGE SUBTASK |  |  |  | 20 | 19/10/2020 | 2020-03-11
| C.R.U.D Subtask | Feature | Milestone_1 | Chương |  | 21/10/2020 | 27/10/2020
| POMODORO |  |  |  | 8 | 25/10/2020 | 2020-06-11 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Set Time | Feature | Milestone_2 | Hằng |  | 25/10/2020 | 2020-02-11
| Set Task | Feature | Milestone_2 | Hằng |  | 25/10/2020 | 2020-02-11
| Extend Time | Feature | Milestone_2 | Hằng |  | 25/10/2020 | 2020-05-11 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Pause Pomodoro | Feature | Milestone_2 | Hằng |  | 25/10/2020 | 2020-05-11 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Break Pomodoro | Feature | Milestone_2 | Hằng |  | 25/10/2020 | 2020-05-11 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Change Task's Status | Feature | Milestone_2 | Hằng |  | 27/10/2020 | 2020-05-11
| View History | Feature | Milestone_2 | Hằng |  | 27/10/2020 | 2020-06-11
Phân Tích Những Rủi Ro của Phần Mềm | View Statistics | Feature | Milestone_2 | Hằng |  | 30/10/2020 | 2020-06-11 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| REMINDER |  |  |  | 8 | 27/10/2020 | 2020-03-11 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Set period of time | Feature | Milestone_3 | Leader |  | 27/10/2020 | 2020-01-11 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Set point of time | Feature | Milestone_3 | Leader |  | 27/10/2020 | 2020-01-11 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Add Reminded Task | Feature | Milestone_3 | Leader |  | 27/10/2020 | 2020-01-11
Del Reminder | Delete Reminded Task | Feature | Milestone_3 | Leader |  | 27/10/2020 | 2020-01-11 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Set Nofications | Feature | Milestone_3 | Leader |  | 29/10/2020 | 2020-02-11
| Set sending email option | Feature | Milestone_3 | Leader |  | 29/10/2020 | 2020-02-11
| View Reminder List | Feature | Milestone_3 | Leader |  | 31/10/2020 | 2020-03-11
| View History | Feature | Milestone_3 | Leader |  | 31/10/2020 | 2020-03-11
| LOGIN & LOGOUT |  |  |  | 3 | 3/11/2020 | 5/11/2020
| Login with username / password | Feature | Milestone_3 | Giang |  | 3/11/2020 | 4/11/2020
| Login with Google Account | Feature | Milestone_3 | Giang |  | 3/11/2020 | 4/11/2020
| Forgot password | Feature | Milestone_3 | Giang |  | 3/11/2020 | 4/11/2020
Chia Các Branch Dev Trên Github | Change Google Account | Feature | Milestone_3 | Giang |  | 4/11/2020 | 2020-05-11
| Register | Feature | Milestone_3 | Giang |  | 3/11/2020 | 2020-04-11
| Logout | Feature | Milestone_3 | Giang |  | 3/11/2020 | 4/11/2020
| REPEATER |  |  |  | 5 | 06/11/2020 | 12/11/2020
| Set Task | Feature | Milestone_4 | Nhữ Hào |  | 06/11/2020 | 09/11/2020
| Set time | Feature | Milestone_4 | Nhữ Hào |  | 06/11/2020 | 07/11/2020
Phân Tích Các Chuẩn Dữ Liệu Của API | Set period of time | Feature | Milestone_4 | Nhữ Hào |  | 08/11/2020 | 09/11/2020
| Set point of time | Feature | Milestone_4 | Nhữ Hào |  | 09/11/2020 | 09/11/2020
| Set time loop | Feature | Milestone_4 | Nhữ Hào |  | 07/11/2020 | 10/11/2020
| View repeated task | Feature | Milestone_4 | Nhữ Hào |  | 06/11/2020 | 12/11/2020
| Cancel repeater | Feature | Milestone_4 | Nhữ Hào |  | 06/11/2020 | 09/11/2020
| USER ACCOUNT MANAGEMENT (ADMIN) |  |  |  | 5 | 9/11/2020 | 12/11/2020
| C.R.U.D Account's Info | Feature | Milestone_4 | Anh |  | 9/11/2020 | 12/11/2020
This is an empty row | Block Account | Feature | Milestone_4 | Anh |  | 9/11/2020 | 12/11/2020
| Unblock Account | Feature | Milestone_4 | Anh |  | 9/11/2020 | 12/11/2020
| Delete Account | Feature | Milestone_4 | Anh |  | 9/11/2020 | 12/11/2020 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| DEFAULT PROJECT MANAGEMENT |  |  |  | 5 | 11/11/2020 | 14/11/2020
| Inbox | Feature | Milestone_5 | Khoa |  | 11/11/2020 | 12/11/2020 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Today | Feature | Milestone_5 | Khoa |  | 12/11/2020 | 13/11/2020
| Tomorrow | Feature | Milestone_5 | Khoa |  | 13/11/2020 | 14/11/2020
| Week | Feature | Milestone_5 | Khoa |  | 13/11/2020 | 14/11/2020 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Upcomming | Feature | Milestone_5 | Khoa |  | 14/11/2020 | 14/11/2020 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
USER INFORMATION MANAGEMENT (USER) | USER INFORMATION MANAGEMENT (USER) |  |  |  | 3 | 15/11/2020 | 18/11/2020 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Change Username | Feature | Milestone_5 | Nhữ Hào |  | 15/11/2020 | 18/11/2020
| Change Password | Feature | Milestone_5 | Nhữ Hào |  | 15/11/2020 | 18/11/2020
| Change Google Account | Feature | Milestone_5 | Nhữ Hào |  | 17/11/2020 | 18/11/2020 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Change Name | Feature | Milestone_5 | Nhữ Hào |  | 15/11/2020 | 18/11/2020
| Change Location | Feature | Milestone_5 | Nhữ Hào |  | 15/11/2020 | 18/11/2020
| Change email | Feature | Milestone_5 | Nhữ Hào |  | 15/11/2020 | 18/11/2020
| SYSTEM NOTIFICATION MANAGEMENT |  |  |  | 5 | 21/11/2020 | 27/11/2020
| Add System Notification | Feature | Milestone_5 | Anh |  | 21/11/2020 | 23/11/2020
| View System Notification | Feature | Milestone_5 | Anh |  | 21/11/2020 | 23/11/2020
| Set Time Sending | Feature | Milestone_5 | Anh |  | 25/11/2020 | 27/11/2020
| Select User Zone | Feature | Milestone_5 | Anh |  | 25/11/2020 | 27/11/2020
| Cancel System Notification | Feature | Milestone_5 | Anh |  | 21/11/2020 | 22/11/2020
| USER NOTIFICATION MANAGEMENT |  |  |  | 5 | 24/11/2020 | 27/11/2020
| View Notification | Feature | Milestone_6 | Khoa |  | 24/11/2020 | 26/11/2020
| View NotificationList | Feature | Milestone_6 | Khoa |  | 24/11/2020 | 26/11/2020
| Hide Notification | Feature | Milestone_6 | Khoa |  | 24/11/2020 | 27/11/2020
| Setting Notification Options | Feature | Milestone_6 | Khoa |  | 24/11/2020 | 27/11/2020
| EXPORT & PRINT | Feature |  |  | 8 | 29/11/2020 | 6/12/2020
| Export chart | Feature | Milestone_6 | Chương |  | 29/11/2020 | 2/12/2020
This row marks the end of the Gantt milestone data. DO NOT enter anything in this row. To add more items, insert new rows above this one. | Export achivement | Feature | Milestone_6 | Chương |  | 29/11/2020 | 2/12/2020
| Export User Account | Feature | Milestone_6 | Chương |  | 29/11/2020 | 2/12/2020
| Export Statistics | Feature | Milestone_6 | Chương |  | 29/11/2020 | 2/12/2020
| Export Completed Task | Feature | Milestone_6 | Chương |  | 29/11/2020 | 2/12/2020
| Print file pdf | Feature | Milestone_6 | Chương |  | 2/12/2020 | 6/12/2020
| Print file image | Feature | Milestone_6 | Chương |  | 2/12/2020 | 6/12/2020
| Export multiple files | Feature | Milestone_6 | Chương |  | 4/12/2020 | 6/12/2020
| STATISTICS |  |  |  | 8 | 7/12/2020 | 15/12/2020
| Completed Task Statistics | Feature | Milestone_7 | Thắng |  | 7/12/2020 | 12/12/2020
| All Task Statistic | Feature | Milestone_7 | Thắng |  | 7/12/2020 | 12/12/2020
| Tag Task Statistics | Feature | Milestone_7 | Thắng |  | 7/12/2020 | 12/12/2020
| Deadline Task Statistics | Feature | Milestone_7 | Thắng |  | 11/12/2020 | 15/12/2020
| Achievement Statistics | Feature | Milestone_7 | Thắng |  | 11/12/2020 | 15/12/2020
| Pomodoro Statistics | Feature | Milestone_7 | Thắng |  | 11/12/2020 | 15/12/2020
| Using App Statistics | Feature | Milestone_7 | Thắng |  | 11/12/2020 | 15/12/2020
| MY CHART |  |  |  | 13 | 7/12/2020 | 14/12/2020
| Add Task | Feature | Milestone_7 | Bôn |  | 7/12/2020 | 8/12/2020
| Move Task | Feature | Milestone_7 | Bôn |  | 7/12/2020 | 8/12/2020
| Set Relationship | Feature | Milestone_7 | Bôn |  | 9/12/2020 | 12/12/2020
| Change Status Task | Feature | Milestone_7 | Bôn |  | 7/12/2020 | 7/12/2020
| Save Chart | Feature | Milestone_7 | Bôn |  | 12/12/2020 | 14/12/2020
| View Chart List | Feature | Milestone_7 | Bôn |  | 7/12/2020 | 8/12/2020
| Delete Chart | Feature | Milestone_7 | Bôn |  | 7/12/2020 | 8/12/2020
ADD FRIENDS | ADD FRIENDS |  |  |  | 3 | 15/12/2020 | 19/12/2020
| Send Invitation | Feature | Milestone_8 | Bôn |  | 15/12/2020 | 16/12/2020
| Accept Invitation | Feature | Milestone_8 | Bôn |  | 15/12/2020 | 17/12/2020
| View Friend List | Feature | Milestone_8 | Bôn |  | 15/12/2020 | 16/12/2020
| Unfriend | Feature | Milestone_8 | Bôn |  | 15/12/2020 | 19/12/2020
RANKING | RANKING |  |  |  | 3 | 17/12/2020 | 19/12/2020
| View ranking list (World) | Feature | Milestone_8 | Leader |  | 17/12/2020 | 18/12/2020
| View ranking list (Friend) | Feature | Milestone_8 | Leader |  | 17/12/2020 | 19/12/2020
| View Current Rank | Feature | Milestone_8 | Leader |  | 17/12/2020 | 18/12/2020
| Increase Score | Feature | Milestone_8 | Leader |  | 17/12/2020 | 19/12/2020
ACHIEVEMENT | ACHIEVEMENT |  |  |  | 5 | 15/12/2020 | 19/12/2020
| View Achievement List | Feature | Milestone_8 | Thắng |  | 15/12/2020 | 16/12/2020
| Record Achievement | Feature | Milestone_8 | Thắng |  | 15/12/2020 | 17/12/2020
| Get Point | Feature | Milestone_8 | Thắng |  | 17/12/2020 | 18/12/2020
| Share Achievement | Feature | Milestone_8 | Thắng |  | 18/12/2020 | 19/12/2020
MY MUSIC | MY MUSIC |  |  |  | 5 | 21/12/2020 | 24/12/2020
| Choose music | Feature | Milestone_9 | Nhật Hào |  | 21/12/2020 | 22/12/2020
| Upload your music | Feature | Milestone_9 | Nhật Hào |  | 21/12/2020 | 24/12/2020
| View list music | Feature | Milestone_9 | Nhật Hào |  | 21/12/2020 | 22/12/2020
| Pause music | Feature | Milestone_9 | Nhật Hào |  | 21/12/2020 | 23/12/2020
| Delete music | Feature | Milestone_9 | Nhật Hào |  | 21/12/2020 | 22/12/2020
| Break music | Feature | Milestone_9 | Nhật Hào |  | 21/12/2020 | 23/12/2020